## Excavation-Trenching
Job Hazard Analysis (JHA)
Activity/Task: EXCAVATION/TRENCHING |  | Overall Risk Assessment Code (RAC) | Overall Risk Assessment Code (RAC) |  | Overall Risk Assessment Code (RAC) |  |  |  | Overall Risk Assessment Code (RAC)
Project & Location: |  | Risk Assessment Code (RAC) Matrix -Severity x Probability = Overall Risk
General Contractor: |  | Severity (Outcome) |  | x |  | Probability (Likelihood) | Overall Risk Rating | Overall Risk
Coffman Job #:
Date: |  | Critical (6) |  | x |  | 4-Very Likely |  | 24-Very High
Project Manager: |  | Major (4) |  | x |  | 3-Likely |  | 8-18-High
Superintendent: |  | Moderate (2) |  | x |  | 2-Possible |  | 4-6- Medium
EHS Manager: |  | Minor (1) |  | x |  | 1-Unlikely |  | 1-3 Low
Review each “Hazard” with identified safety “Controls” and determine RAC (See above)
Never Authorized | [6 empty] | WHO CAN AUTHROIZE HAZARDOUS ACTIVITIES
Operations Manager (General Supt/Project Executive/EHS Program Mgr)
SR.PM/Lead Supt/Site EHS Manager
Supt/EHS Manager/PM
Job Steps | Hazards |  | Controls | [6 empty] | Severity Probability Risk
1. Mobilize Equipment To & From Site | 1.1 Struck by Equipment |  | 1.1.1 Follow all posted speed limits and guidelines on and off campus | [6 empty] | 2 x 1 = 2
|  |  | 1.1.2 Use spotters when loading and unloading equipment, to ensure people are not in the loading and unloading zone. | [6 empty] | 2 x 1 = 2
|  |  | 1.1.3 All personnel to class 2 wear high visibility vest/shirt and safety toed work boots, minimum 6" tall. | [6 empty] | 2 x 1 = 2
|  |  | 1.1.4 Use spotter to help ensure equipment has a clear path on and off of truck watching for other trades and pedestrians. | [6 empty] | 2 x 1 = 2
| 1.2 Fuel Spills |  | 1.2.1 Spill kit readily available on truck and onsite | [6 empty] | 2 x 1 = 2
| 1.3 Low Visibility |  | 1.3.1 Ensure headlights are in working order | [6 empty] | 2 x 1 = 2
|  |  | 1.3.2 All personnel to class 2 wear high visibility vest/shirt. | [6 empty] | 2 x 1 = 2
|  |  | 1.3.3 Ensure windshield/mirrors along with wipers are in proper working order and clean | [6 empty] | 2 x 1 = 2
| 1.4 Loading & Unloading Machinery |  | 1.4.1 Ensure load is secured to vehicle | [6 empty] | 2 x 1 = 2
|  |  | 1.4.2 Vehicle to be parked on flat and level ground prior to loading and unloading | [6 empty] | 2 x 1 = 2
|  |  | 1.4.3 Use spotter to help ensure equipment has a clear path on and off of truck watching for other trades and pedestrians. | [6 empty] | 2 x 1 = 2
2. Perform Equipment Inspections | 2.1 Awkward Posture/Positioning When Inspecting |  | 2.1.1 Stretch and Flex prior to starting work. | [6 empty] | 2 x 1 = 2
|  |  | 2.12 Perform inspections at surface level, when possible. | [6 empty] | 2 x 1 = 2
| 2.2 Pinch Points |  | 2.2.1 Proper positioning of equipment. | [6 empty] | 2 x 1 = 2
|  |  | 2.2.2 Beware of hand/body placement. | [6 empty] | 2 x 1 = 2
| 2.3 Unauthorized Starting of Equipment |  | 2.3.1 Verify keys are not in the ignition. | [6 empty] | 2 x 1 = 2
3. Site Excavation | 3.1 Moving Rotating Equipment |  | 3.1.1 Equipment equipped with warning devices such as back-up alarms or ATB devices. | [6 empty] | 4 x 1 = 4
| 3.2 Struck By/Caught Between Equipment |  | 3.2.1 Only authorized operators to use equipment. | [6 empty] | 4 x 1 = 4
|  |  | 3.2.2 Spotter | [6 empty] | 4 x 1 = 4
| 3.3 Damage to Equipment/Existing Structures |  | 3.3.1 Spotter | [6 empty] | 4 x 1 = 4
|  |  | 3.3.2 Maintain clearance from overhead wires/obstructions. | [6 empty] | 4 x 1 = 4
3.3.3 Use barricades when needed to protect existing structures and equipment
|  |  | 3.3.4 Utilize Utility Awareness form for existing utilities above and below ground | [6 empty] | 4 x 1 = 4
| 3.4 Tipping of Equipment |  | 3.4.1 Equipment will be matched to the intended loads for weight, size and activity. | [6 empty] | 4 x 1 = 4
|  |  | 3.4.2 Employees, other trades and pedestrians will keep clear of loading/hoisting operations. | [6 empty] | 4 x 1 = 4
|  |  | 3.4.3 PPE- Class 2 High-viz clothing. | [6 empty] | 4 x 1 = 4
|  |  | 3.4.4 Spotter to keep either verbal, visual (eye contact) or hand signal contact with operator. | [6 empty] | 4 x 1 = 4
|  |  | 3.4.5 Equipment to maintain safe distance from edge of trench/excavation. | [6 empty] | 4 x 1 = 4
| 3.5 Cave-ins |  | 3.5.1 Competent person to inspect excavation/trench daily or when site conditions or weather changes throughout the day. | [6 empty] | 4 x 1 = 4
|  |  | 3.5.2 Used engineered shoring, shielding system, sloping or benching when excavation/trench is over 5' or as needed at lesser depth. | [6 empty] | 4 x 1 = 4
3.5.3 Keep Spoils 2 feet back from edge of trench.
| 3.6 Ground Erosion |  | 3.6.1 Cover dirt slopes and install erosion control measures as needed. | [6 empty] | 4 x 1 = 4
| 3.7 Fall hazards >6' |  | 3.7.1 Secure area with red rope/hard barricade. | [6 empty] | 4 x 1 = 4
3.7.2 Utilize fall protection equipment when required.
| 3.8 Striking Existing Utilities |  | 3.8.1 Call for locates private/public prior to the start of work. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.2 Refer to plan set/asbuilts prior to start of work. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.3 Check with other trades about where their utilities are located prior to starting work. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.4 Check with GC about changes that may have been made to plans/asbulits prior to starting work. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.5 Pothole prior to the start of work when able. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.6 Do not mechanically dig when within 3 feet of known utilities. Hand dig with shovel or use vac-ex. | [6 empty] | 4 x 1 = 4
|  |  | 3.8.7 Complete Coffman's Utility Awareness form and review with crew prior to the start of work. This will include above and below ground utilities. | [6 empty] | 4 x 1 = 4
4. Haul off debris/soil dump truck | 4.1 Struck By/Caught Between Equipment & Truck |  | 4.1.1 PPE- Class 2 High-viz clothing. | [6 empty] | 4 x 1 = 4
|  |  | 4.1.2 Spotter to stay out of swing radius of excavator. | [6 empty] | 4 x 1 = 4
|  |  | 4.1.3 Spotter to keep either verbal, visual (eye contact) or hand signal contact with operator. | [6 empty] | 4 x 1 = 4
| 4.2 Equipment/Truck Collision |  | 4.2.1 Equipment/Trucks to be directed by spotters when needed for trucks to enter/exit safely. | [6 empty] | 4 x 1 = 4
|  |  | 4.2.2 Seat belts to be worn in equipment/trucks when equipment/trucks is equipped with such. | [6 empty] | 4 x 1 = 4
| 4.3 Falling Material |  | 4.3.1 Trucks will be loaded below top of side rails with no material on side rails. | [6 empty] | 4 x 1 = 4
|  |  | 4.3.2 Spotter to remove debris from side rails, prior to truck leaving site. | [6 empty] | 4 x 1 = 4
|  |  | 4.3.3 Spotter to check duals of trucks for rocks. | [6 empty] | 4 x 1 = 4
| 4.4 Equipment/Property Damage |  | 4.4.1 Only authorized operators to use equipment. | [6 empty] | 4 x 1 = 4
|  |  | 4.4.2 Spotters to be used in areas where equipment may be a danger to others/property. | [6 empty] | 4 x 1 = 4
| 4.5 Dust |  | 4.5.1 Maintain dust utilizing water truck or other on-site water source. | [6 empty] | 4 x 1 = 4
5. Fueling Equipment | 5.1 Chemical Exposure, Spills & Unidentified Ignition Source |  | 5.1.1 Review SDS (Coffman's SDSs can be found on the QR code) and understand hazards of the chemicals being used. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.2 Use proper gloves for fueling. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.3 Keep potential ignition source a minimum of 25' from fueling area. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.4 Fire extinguisher readily available in fueling area. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.5 Spill kit on site and/or on fuel truck. | [6 empty] | 2 x 1 = 2
| 5.2 Struck-By/Caught Between Equipment |  | 5.2.1 Only authorized operators to operate equipment. | [6 empty] | 2 x 1 = 2
|  |  | 5.2.2 Use spotters when needed. | [6 empty] | 2 x 1 = 2
| 5.3 Slippery Equipment/Ground Conditions Due To Wet/Freezing Weather, Mud, Lose Rock. |  | 5.3.1 Utilize 3 points of contact when climbing on and off equipment. | [6 empty] | 2 x 1 = 2
|  |  | 5.3.2 Evaluate work area prior to starting work. | [6 empty] | 2 x 1 = 2
Verification of Review
Name (Print) |  | Signature |  |  |  | Date
Superintendent:
Project Manager:
EHS: Amy McClean
Foreman:
Crew Member:
Crew Member:
Crew Member:
Crew Member:
Crew Member: