## Vac-Exing
Job Hazard Analysis (JHA)
Activity/Task: VAC-EXING |  | Overall Risk Assessment Code (RAC) | Overall Risk Assessment Code (RAC) |  | Overall Risk Assessment Code (RAC) |  |  |  | Overall Risk Assessment Code (RAC)
Project & Location: |  | Risk Assessment Code (RAC) Matrix -Severity x Probability = Overall Risk
General Contractor: |  | Severity (Outcome) |  | x |  | Probability (Likelihood) | Overall Risk Rating | Overall Risk
Coffman Job #:
Date: |  | Critical (6) |  | x |  | 4-Very Likely |  | 24-Very High
Project Manager: |  | Major (4) |  | x |  | 3-Likely |  | 8-18-High
Superintendent: |  | Moderate (2) |  | x |  | 2-Possible |  | 4-6- Medium
EHS Manager: |  | Minor (1) |  | x |  | 1-Unlikely |  | 1-3 Low
Review each “Hazard” with identified safety “Controls” and determine RAC (See above)
Never Authorized | [6 empty] | WHO CAN AUTHROIZE HAZARDOUS ACTIVITIES
Operations Manager (General Supt/Project Executive/EHS Program Mgr)
SR.PM/Lead Supt/Site EHS Manager
Supt/EHS Manager/PM
Job Steps | Hazards |  | Controls | [6 empty] | Severity Probability Risk
1. Perform Equipment Inspections | 1.1 Awkward Posture/Positioning When Inspecting |  | 1.1.1 Stretch and Flex prior to starting work. | [6 empty] | 2 x 1 = 2
|  |  | 1.1.2 Perform inspections at surface level, when possible. | [6 empty] | 2 x 1 = 2
| 1.2 Pinch Points |  | 1.2.1 Proper positioning of equipment. | [6 empty] | 2 x 1 = 2
|  |  | 1.2.2 Beware of hand/body placement. | [6 empty] | 2 x 1 = 2
2. Equipment Set-up | 2.1 Moving/Rotating Equipment |  | 2.1.1 Equipment equipped with back-up alarms. | [6 empty] | 2 x 2 = 4
|  |  | 2.1.2 Only authorized persons to operator equipment. | [6 empty] | 2 x 2 = 4
| 2.2 Struck By/Caught By-hoses, equipment, structures |  | 2.2.1 Spotter when moving/working near buildings, structures or other personnel. | [6 empty] | 2 x 2 = 4
|  |  | 2.2.2 Maintain 10ft distance from overhead wires. | [6 empty] | 2 x 2 = 4
|  |  | 2.2.3 PPE- Class 2 High-viz clothing. | [6 empty] | 2 x 2 = 4
|  |  | 2.2.4 Spotter to maintain eye contact with operator/driver. | [6 empty] | 2 x 2 = 4
| 2.3 Tipping Of Equipment-Cave-Ins |  | 2.3.1 Equipment to say a safe distance away from the excavation (a minimum of 2 feet). | [6 empty] | 2 x 2 = 4
|  |  | 2.3.2 Use of engineered shoring, shielding, sloping or benching to help prevent cave-ins, when excavation/trench is over 5' deep, or if conditions demand. | [6 empty] | 2 x 2 = 4
3. Operating Vac-ex | 3.1 Struck-by Hose |  | 3.1.1 Keep all unnecessary personnel, bystanders, and pedestrians out of work area, by using red rope, spotter, or hard barricade. | [6 empty] | 2 x 2 = 4
|  |  | 3.1.2 Review controls and familiarize yourself with them before the start of work. | [6 empty] | 2 x 2 = 4
| 3.2 Excessive Suction and Water Pressure |  | 3.2.1 Keep suction hose away from face and other body parts. | [6 empty] | 2 x 4 = 8
|  |  | 3.2.2 Inspect and insure connections are tight prior to the start of high pressure suction. | [6 empty] | 2 x 4 = 8
|  |  | 3.2.3 Replace defective or warn parts. | [6 empty] | 2 x 2 = 4
|  |  | 3.2.4 Know where the kill switch is and let anyone you are working with know where the kill switch is. | [6 empty] | 2 x 2 = 4
|  |  | 3.2.5 Face shield and safety glass for excess Flying debris. | [6 empty] | 2 x 2 = 4
|  |  | 3.2.6 Maintain adequate distance form existing utility. | [6 empty] | 2 x 2 = 4
|  |  | 3.2.7 Keep water lance in motion when vac-exing. | [6 empty] | 2 x 2 = 4
4. Vax-exing Near, Around or For Existing Utilities | 4.1 Striking existing utility |  | 4.1.1 Call for locates private and or public prior to the start of work. | [6 empty] | 2 x 2 = 4
|  |  | 4.1.2 Refer to Plan-set/Asbuilts prior to the start of work. | [6 empty] | 2 x 2 = 4
|  |  | 4.1.3 Check with other trades on where their utilities may be located prior to start of work. | [6 empty] | 2 x 2 = 4
|  |  | 4.1.4 Check with GC about any changes to utilities that may have been made prior to plan-set/asbuilts being sent out. | [6 empty] | 2 x 2 = 4
|  |  | 4.1.5 Complete Coffman's Utility Awareness form and review with crew prior to the start of work. This will include above and below ground utilities. | [6 empty] | 2 x 2 = 4
| 4.2 Open hole fall >6' |  | 4.2.1 Install hard barricade as fall protection. | [6 empty] | 2 x 2 = 4
|  |  | 4.2.2 Tie off with rope/retractable and harness for fall restraint or arrest. | [6 empty] | 2 x 2 = 4
| 4.3 Excessive noise over 85db |  | 4.3.1 PPE hearing protection. | [6 empty] | 2 x 2 = 4
| 4.4 Sharp Edges |  | 4.4.1 PPE Level 3 Cutless gloves.
4.4.2 Tape or pad off sharp edges.
5. Fueling Equipment | 5.1 Chemical Exposure, Spills & Unidentified Ignition Source |  | 5.1.1 Review SDS (Coffman's SDSs can be found on the QR code) and understand hazards of the chemicals being used. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.2 Use proper gloves for fueling. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.3 Keep potential ignition source a minimum of 25' from fueling area. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.4 Fire extinguisher readily available in fueling area. | [6 empty] | 2 x 1 = 2
|  |  | 5.1.5 Spill kit on site and/or on fuel truck. | [6 empty] | 2 x 1 = 2
| 5.2 Struck-By/Caught Between Equipment |  | 5.2.1 Only authorized operators to operate equipment. | [6 empty] | 2 x 1 = 2
|  |  | 5.2.2 Use spotters when needed. | [6 empty] | 2 x 1 = 2
| 5.3 Slippery Equipment/Ground Conditions Due To Wet/Freezing Weather, Mud, Lose Rock. |  | 5.3.1 Utilize 3 points of contact when climbing on and off equipment. | [6 empty] | 2 x 1 = 2
|  |  | 5.3.2 Evaluate work area prior to starting work. | [6 empty] | 2 x 1 = 2
Verification of Review
Name (Print) |  | Signature |  |  |  | Date
Superintendent:
Project Manager:
EHS:
Foreman:
Crew Member:
Crew Member:
Crew Member:
Crew Member:
Crew Member: